## Task Tracker
TASK TRACKER
Name: | Shubham Mevada |  |  |  | Date: | 26th July 2021
TASK TITLE | STATUS | PRIORITY | START DATE | DUE DATE | PCT OF TASK COMPLETE | COMMENTS | STATUS MENU | PRIORITY MENU
ER- Diagram Model | ☒ | HIGH | 2021-07-27 | 2021-07-30 | 100% |  | ☐ | HIGH
Forwadr Engineering | ☒ | MEDIUM | 2021-07-31 | 2021-07-31 | 100% |  | ☒ | MEDIUM
Data Insertion | ☒ | HIGH | 2021-08-02 | 2021-08-03 | 100% |  |  | LOW
Event/Triggers | ☒ | MEDIUM | 2021-08-04 | 2021-08-04 | 100%
Insertion of Quries | ☒ | HIGH | 2021-08-05 | 2021-08-05 | 100%
Specific Scenario quries from user point of view | ☒ | HIGH | 2021-08-06 | 2021-08-06 | 100%
Backup Database | ☒ | HIGH | 2021-08-07 | 2021-08-07 | 100%
Technical Report | ☒ | HIGH | 2021-08-10 | 2021-08-10 | 100%
Power Point Presentation | ☒ | HIGH | 2021-08-15 | 2021-08-15 | 100%
Uploading Final Project File | ☒ | HIGH | 2021-08-16 | 2021-08-16 | 100%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
100%